## Slide 1
Transnational conference with Stakeholders and General Public
Foggia 28.02.2025
Municipality of Fasano, Giuseppe Pugliese
Next steps on ADRIAMOVE
Forthcomings activities …..

## Slide 2
📌 Objective:
Comprehensive understanding of the context, challenges, and good practices in sustainable mobility across the Adriatic-Ionian
Preparation for the upcoming activities of WP2
WP 1
Common Territorial Mapping on Sustainable Mobility
Duration: 36 month (start 01/09/2024)
Budget : € 1.497.083,22
Interreg Found: € 1.272.520,73 (85%)
WP 2
Intermodal Pilot Actions
WP 3
Awareness Campaigns and Stakeholder Engagement
📌 Objective:
Implementation of Pilot actions across the 6 municipalities : Fasano (IT) – Dugopolje (HR) – Postojna (SI) – Gjirokaster (AL) - Centar Sarajevo (BA) – Budva (ME)
📌 Objective:
Enhance awareness, stakeholder engagement, and strategic planning for sustainable and intermodal mobility in the project areas.
Period:
From 01/09/24
To 31/08/26
Period:
From 01/09/25
To 28/02/27
Period:
From 01/09/24
To 31/08/27

## Slide 3
WP 1
Common Territorial Mapping on Sustainable Mobility
Activities | Deliverables | Period
1.1. Transnational conference Held in Foggia Gather local authorities, transport operators, experts, civil society, and the public to discuss sustainable mobility. | Media kit and Collection of documents of the transnational conference (including: agenda, documents, information materials, meeting summaries …) | by end of February 2025
 | Promotional video (audiovisual production to introduce and showcase the ADRIAMOVE project to a wide audience) – Created by Foggia and Vlore Universities | by end of August 2025
 | Creation of a network that will continue working after the project finalisation | by end of February 2026
1.2. Analysis of Context and Good Practices in the Adriatic-Ionian areas The objective is to assess transport and mobility in the Adriatic-Ionian region…. understand existing infrastructure, policies, and practices to identify challenges, opportunities, and good practices and solutions | A detailed analysis of countries in the Adriatic-Ionian region to find the best examples of green transportation. | by end of February/March 2025
 | A Joint report on urban mobility in the area (explaining the main problems each country faces, like traffic, air pollution, poor infrastructure, and limited accessibility) - Leaded by Foggia and Vlore Universities | by end of August 2025

## Slide 4
Activities | Deliverables | Period
1.3. Study visits to best practices - Italy and Montenegro Visits in two cities (Italy and Montenegro) with relevant best practices in mobility. Organized by Fasano and Budva. Observe real examples, visit key mobility projects, meet local experts and policy makers. The goal is to understand innovative solutions, and gain practical knowledge. For each study visit, a total of 16 participants ( 1 internal staff member and 1 stakeholder from the mobility or environmental sector) | Study visits kits (a set of documents, including reports, key results, materials, and agendas. | from Sept 2025 until Febr 2026
 | Promotional video press of the study visits (highlighting important moments, activities, and experiences from the visits, showing the mobility solutions, best practices, and challenges in sustainable urban transport) | from Sept 2025 until Febr 2026
1.4. Transnational and Local Sessions about Sustainable Mobility Includes two types of training on sustainable mobility. N. 3 training sessions (the first in Foggia (PP2), the second online, and the third in Vlore (PP6), Addressed mainly to Mobility Manager (two members per partner) N. 12 training sessions (two per each municipality) Addressed to stakeholders (at least eight per session). Training will cover key topics like transport solutions, policies, planning, and funding to help apply sustainable mobility practices locally. | Training Sessions Kit (agenda, training modules, content of the sessions) A complete guide for trainers and participants (provided by the hosting partners) | from March 2026 until August 2026
 | Report on the transnational and local training sessions | from March 2026 until August 2026
WP 1
Common Territorial Mapping on Sustainable Mobility

## Slide 5
Activity 2.2
Pilot Actions: Multimodal Service Development in the different regions
WP 2
Intermodal Pilot Actions
Specific emphasis on fostering and demonstrate the feasibility of sustainable mobility options
A total of 6 pilot action will be implemented – one of each municipality:
Fasano, Dugopolje, Centar Sarajevo Electric buses
Gjirokaster, and Budva Tuktuk for touristic purposes
Postojna Electric bicycles system
Start period: March 2026 – August 2026
End period: September 2026 – February 2027

## Slide 6
“Crosscutting activity”
The network brings together experts and stakeholders
Created at the start of the project until the end
Main task:
Provide recommendations, share knowledge and find solutions
Serves as a platform for regular discussions, consultations, and strategic decision making
Promote cooperation
WP 3 - Awareness Campaigns and Stakeholder Engagement
Activity 3.1 Transnational Permanent Advisory Board on Sustainable and Intermodal Mobility

## Slide 7
OUTPUT | Activities | Deliverables | Starts month | End month | End Period
 | A 1.1. Transnational conference with Stakeholders and General Public |  | 01/09/24 | 28/02/25 | Period 1
 |  | D 1.1.1. Media kit produced by the project | 01/09/24 | 28/02/25 | Period 1
 |  | D.1.1.2 Launching video of the project | 01/09/24 | 31/08/25 | Period 2
 |  | D.1.1.3 Documents of the trans national conference | 01/09/24 | 28/02/25 | Period 1
 |  | D.1.1.4 Transnational Network on Urban Sustainable Mobility | 01/09/24 | 28/02/26 | Period 3
 | A 1.2. Analysis of Context and Good Practices in the Adriatic-Ionian areas |  | 01/09/24 | 31/08/25 | Period 2
 |  | D.1.2.1 Identification of countries with good practices in green transports | 01/09/24 | 31/08/25 | Period 2
 |  | D.1.2.2 Joint report on the context and reality on urban mobility of the Countries involved | 01/09/24 | 31/08/25 | Period 2
 | A 1.3. Study visits to the countries with best practices - Italy and Montenegro |  | 01/03/25 | 31/08/25 | Period 2
 |  | D.1.3.1 Study visits kits | 01/03/25 | 28/02/26 | Period 3
 |  | D.1.3.2 Promotional video press of the study visits | 01/03/25 | 28/02/26 | Period 3
 | A 1.4. Transnational Sessions about Sustainable Mobility for partners and Local Training sessions for stakeholders |  | 01/09/24 | 28/02/26 | Period 3
 |  | D.1.4.1 International Training Sessions Kit (agenda, training modules, content of the sessions) | 01/09/24 | 31/08/26 | Period 4
 |  | D.1.4.2 Report on Transnational Sessions for ADRIAMOVE partners about Sustainabl Mobility | 01/09/24 | 31/08/26 | Period 4
 |  | D.1.4.3 Report on Local Training sessions for stakeholders about Sustainable Mobility | 01/09/24 | 31/08/26 | Period 4
Output 1.1 Transnational Network on Urban Sustainable Mobility |  |  | 01/09/24 | 28/02/26 | Period 3
 | A 3.1 Transnational Permanent Advisory Board on Sustainable and Intermodal Mobility |  | 01/09/24 | 28/02/26 | Period 3
 |  | D.3.1.1 Transnational Permanent Advisory Board on Sustainable and Intermodal Mobility | 01/09/24 | 28/02/25 | Period 1
 |  | D.3.1.2 Meeting Reports on the three meetings of the board | 01/09/24 | 28/02/26 | Period 3
 |  | D.3.1.3 Guidelines for involving citizens in sustainable transport initiatives | 01/09/24 | 31/08/26 | Period 4
 |  | D.3.1.4 Final recommend dations for the Transnational Permanent Advisory Board | 01/09/24 | 31/08/26 | Period 4

## Slide 8
Thank you!
28/02/2025
by Giuseppe Pugliese
Lead Partner Municipality of FASANO